## Plan SMA Gabungan
STRATEGICAL PLAN FOR DEVELOPMENT OF SMA GABUNGAN IN JAYAPURA, PERIOD 2007- 2009
No. | Rencana Strategie Global strategic plan | Program Strategis Detailed Strategic Plan | Rincian Program Action Plan | Waktu Period |  |  | Anggaran / Dara Budget | Realisasi Realization | Penanggung Jawab Responsible person | Keterangan Comments
I | INVESTASI:
1 | Adjustment of Legal Documents SMA Gabungan | 1.1. Revision of thee budget based on 1957 Akte notaris | 1.1.1. Consulting with founders 1.1.2. Establish new regulation concerning SMA 1.1.3. Legalization of foundation's rules | 2007 2007 01-08-2007 |  |  | 5.000.000 10.000.000 |  | Chairman Secretary Secretary
2 | Strengthen the foundation | 2.1 Reorganization of the foundation | 2.1.1. Discussing proposals for regulization regarding staffing | 2007 |  |  | 5.000.000 |  | Executive secretary
|  |  | 2.1.2. Proposal to be approved by founders | 2007 |  |  |  |  | Executive secretary
|  |  | 2.1.3. Proposal to be agreed by Dinas Tenaga Kerja Provinsi / Kota (department of labour) | 2007-12-20 |  |  | 2.500.000 |  | Executive secretary
|  |  | 2.1.4. Inform all persons concerned regarding the regulations (send copies) | 2007 |  |  | 2.000.000 |  | Treasurer
|  |  | 2.1.5. Inform and explain the School Team regarding regulations | 2007 |  |  | 1.000.000 |  | Vice Chairman
|  | 2.2. Alumni | 2.2.1. Get alumni involved | 2007 | 2008 | 2009 |  |  | Chairman
3 | Financial arrangement | 3.1. Getting fundeing from various sources | 3.1.1. Donations by alumni | 2007 | 2008 | 2009 | 500.000 |  | Chairman
|  |  | 3.1.2. Sending propsal to Government | 2007 | 2008 | 2009 | 1.000.000 |  | Vice Chairman
|  |  | 3.1.3. Lobby alumni who are member of the council of Papua | 2007 | 2008 | 2009 |  |  | Chairman
|  |  | 3.1.4. Try to establish business activities to get funding | 2007 | 2008 | 2009 |  |  | Secretary
|  |  | 3.1.5. Set up web site to promote SMA Gabungan | 2007 | 2008 | 2009 | 15.000.000 |  | Secretary
4 | Improve level of education | 4.1. Increase quality of students | 4.1.1. Extra schooling of students on mathematics, physics, chemics, biology, social sciences | 2007 | 2008 | 2009 | 120.000.000 |  | Vice chairman | Classes XI, XII
5 | Improve level of teachers and staff | 5.1. Improve facilities | 5.1.1. Provide teachers' library | 2007 | 2008 | 2009 | 35.000.000 |  | Secretary
|  | 5.2. Head Master | 5.2.1. Increase Head Master's professionalism; | 2007 | 2008 | 2009
|  |  | 5.2.2. Organize training and coaching of Head Master | 2007 | 2008 | 2009 | 10.000.000 |  | Vice Chairman
|  | 5.3. Teacher | 5.3.1. Recommend to gouvernment: post education needed by Gouvernment's teachers | 2007 | 2008 | 2009 | 1.000.000 |  | Vice Chairman
|  |  | 5.3.2. Organize training and coaching of teachers | 2007 | 2008 | 2009 | 5.000.000 |  | Vice Chairman
|  |  | 5.3.3. Properity and social funds | 2007 | 2008 | 2009 | 170.000.000 |  | Treasurer
|  | 5.4. Staff of administration department | 5.4.1. Training and development | 2007 | 2008 | 2009 | 6.000.000 |  | Secretary
6 | Infrastructure | 6.1. Provide and improve infrastructure | 6.1.1. Re-measuring/re-mapping SMA ground by Land-Register | 2007 |  |  | 5.000.000 |  | Chairman
|  |  | 6.1.2. Enforcing illeigal inhabitants to stay away from school surroundings | 2007 | 2008 | 2009 | 300.000.000 |  | Caretaker
|  |  | 6.1.3. Build school gates | 2007 |  |  | 7.000.000 |  | Chairman
|  |  | 6.1.4. Build wall around the school | 2007 | 2008 |  | 300.000.000 |  | Chairman
|  |  | 6.1.5. Make path aside of the wall | 2007 | 2008 | 2009 | 100.000.000 |  | Chairman
|  |  | 6.1.6. Establish drainage | 2007 |  |  | 100.000.000 |  | Chairman
|  |  | 6.1.7. Maintenance of buildings and classes | 2007 | 2008 | 2009 | 50.000.000 |  | Chairman
|  |  | 6.1.8. Build SMA Gabungan hall/auditorium | 2007 | 2008 | 2009 | 5.000.000.000 |  | Chairman | Control activities, Lab
|  |  | 6.1.9. Providing cars for operational activities | 2007 | 2008 | 2009 | 16.000.000 |  | Chairman
|  |  | 6.1.10. Maintenance for Language, Physics, Biology, Chemistry and Computer Laboratory | 2007 | 2008 | 2009 | 750.000.000 |  | Secretary
|  |  | 6.1.11. Providing books for school library | 2007 | 2008 | 2009 | 130.000.000 |  | Secretary
|  |  | 6.1.12. Providing books for foundation library | 2007 | 2008 | 2009 | 5.000.000 |  | Secretary
|  |  | TOTAL INVESTMENTS I |  |  |  | 7.126.500.000
II | OPERASIONAL
1 | Operational budget | 1.1. School operational budget | 1.1.1. Expenses of school staff (uniforms, flowers at funerals etc) | 2007 | 2008 | 2009 | 100.000.000 |  | Treasurer
|  |  | 1.1.2. Office requirements expenses | 2007 | 2008 | 2009 | 75.000.000 |  | Treasurer
|  |  | 1.1.3. General expenses | 2007 | 2008 | 2009 | 50.000.000 |  | Treasurer
|  |  | 1.1.4. Routine expenses | 2007 | 2008 | 2009 | 375.000.000 |  | Treasurer
|  | 1.2. Foundation operational expenses | 1.2.1. Expenses for foundation's staff | 2007 | 2008 | 2009 | 20.000.000 |  | Treasurer
|  |  | 1.2.2. Office requirements expenses | 2007 | 2008 | 2009 | 15.000.000 |  | Treasurer
|  |  | 1.2.3. General expenses | 2007 | 2008 | 2009 | 5.000.000 |  | Treasurer
|  |  | 1.2.4. Routine expenses | 2007 | 2008 | 2009 |  |  | Chairman
|  | 1.3. School committee | 1.3.1. Meeting stdents' parents | 2007 |  |  | 6.000.000 |  | Chairman
|  | 1.4. Meetings of SMA's Executive Management | 1.4.1. Planning, organizing, actuating, controlling and evaluation
|  | 1.5. Meetings of SMA's Executive Management with inspectors and founders | 1.5.1. Financial and program report from the foundation and input from the inspectors | 2007 |  |  | 1.000.000 |  | Treasurer
|  |  | 1.5.2. Progress report, evaluation and follow up | 2007 | 2008 | 2009 |  |  | Secretary
|  | 1.6. Deployment amongst school and school committee | 1.6.1. Explanation of policy, system and work mechanism of the Foundation | [5 empty] | Chairman
|  |  | 1.6.2. Feed back from school and school committee | 2007 |  |  |  |  | Chairman
|  | 1.7. Deployment amongst Executive, Inspector and Alumni | 1.7.1. Visits to officials ex-SMA Gabungan Alumni | 2007 |  |  | 70.000.000 15.000.000 |  | Secretary Secretary | Papua Jakarta
|  |  | 1.7.2. SMA Gabungan anniversary | 2007 | 2008 | 2009 | 10.000.000 |  | Secretary
|  |  | 1.7.3. SMA Gabungan Christmas celebration | 2007 | 2008 | 2009 | 5.000.000 |  | Secretary
|  |  | 1.7.4. SMA Gabungan Easter celebration | 2007 | 2008 | 2009 | 5.000.000 |  | Secretary
|  | 1.8. Strengthen financial management | 1.8.1. Set up comprehensive financial administration | 30-06-2007 | 2008 | 2009 | 15.000.000 |  | Treasurer
|  |  | 1.8.2. Socialization of financial policy to SMA Gabungan | 07-2007 |  |  | 1.000.000 |  | Treasurer
|  |  | 1.8.3. Conducting financial audit on Foundation and SMA Gabungan | 2007 | 2008 | 2009 | 3.000.000 |  | Chairman
|  | 1.9. Improvement of students' quality | 1.9.1. Selection of new students | 2007 | 2008 | 2009 | 6.000.000 |  | Vice Chairman
|  |  | 1.9.2. Encouraging spiritual, Christian, art, sport and education value | 2007 | 2008 | 2009 | 35.000.000 |  | Vice Chairman
|  |  | 1.9.3. Socialization of new entering students - policy towards parents | 2007 | 2008 | 2009
|  | 1.10. Relationship development | 1.10.1. Visits to officials ex SMA student | 2007 |  |  | 70.000.000 15.000.000 |  | Secretary Secretary | Papua Jakarta
|  |  | 1.10.2. SMA anniversary | 2007 | 2008 | 2009 | 10.000.000 |  | Secretary
|  |  | 1.10.3. Christmas celebration SMA Gabungan | 2007 | 2008 | 2009 | 5.000.000 |  | Secretary
|  |  | 1.10.4. Easter celebration SMA Gabungan | 2007 | 2008 | 2009 | 5.000.000 |  | Secretary
|  | 1.11. Strenghthen financial management | 1.11.1. Arranging comprehensive financial administration system | 30-06-2007 |  |  | 15.000.000 |  | Tresurer
|  |  | 1.11.2. Socialization of financial management of the Foundation to SMA | 07-2007 |  |  | 1.000.000 |  | Tresurer
|  |  | 1.11.3. Conducting financial audit on Foundation and thee school | 2007 | 2008 | 2009 | 3.000.000 |  | Chairman
1.002.000.000
TOTALS
|  |  | TOTAL I (INVESTASI) |  |  |  | 7.126.500.000
|  |  | TOTAL II (OPERASIONAL) |  |  |  | 1.002.000.000
|  |  | TOTAL GENERAL |  |  |  | 8.128.500.000
|  | Ketua, Chairman <signed on original paper> Paschalis Fau'ubun |  |  |  | Hormat kami, Faithfully yours, Sekretaris Secreatary <signed on original paper> P. C. Nunsius